## Instructions
CEIS390 Risk Register Workbook Instructions
This Risk Register template is to be used for identifying risks and creating plans for how to avoid them (negative risks) or how to make them happen (positive risks) and what to do if they happen (contingency plans) and managing them throughout the project.
NOTE: The best approach to divide the work is to assign each team member a specific number of risk (for example, John has negative risk 1–5 and Venus has negative risk 6–10. This information is needed in order to assess each individual's contribution, which you will state in your individual journal log table.
The first sheet, titled Risk Register, shows a number of fields to use for gathering the following information about risks.
Risk ID is some unique value that identifies the risk.
Risk Name is a short description of the risk.
Risk Description: "If this risk occurs, then what impact will it have on the project?" It should be written as an If-then statement.
Impact as rated on a very low, low, medium, high, and very high scale.
Probability as rated on a very low, low, medium, high, and very high scale.
Risk Ranking: Using the risk matrix found on the right on the Risk Register sheet, detemine the color code (risk ranking) for each risk.
Positive/Negative: Is this risk a positive risk (an opportunity) or a negative risk?
Proactive Response Plan is a detailed plan of what changes will be made to the project, project scope, and/or WBS proactively to try to make the risk happen (positive risk) or stop it if it is a negative risk.
Trigger Event is a description of how you will know if the risk has occurred or is about to occur.
Reactive Contingency Plan is the description of what you plan to do if the risk happens. How will you react to the risk once it has occurred?

## Team#-Risk Register
CEIS390: Week 5—Risk Register
ID | Risk Name | Risk Description | Impact | Probability | Risk Ranking | Positive/Negative | Proactive Response Plan | Trigger Event | Reactive Contingency Plan
|  |  | VH,H,M,L,VL | VH,H,M,L,VL | What is the risk color code ? | Is this a positive or negative risk from the risk matrix? | What proactively can be attempted to make the risk happen or prevent it? | What do you think will trigger the event? | What are your backup plans if the risk should occur?
1 | Employee Turnover | Key personnel leave the project taking critical information with them that significantly delays or derails the project | H | M | Yellow | Negative | Increased collabroation and information sharing on project team. Techniques for better information sharing used can include pair programming, common code ownership, and frequent reporting at daily stand-ups. | Personnel informing project leaders that they are planning to leave | Project Leader will take out time to bring new project members or remaining project members up to speed to address gaps of leaving personnel.
2 | Changing requirements and priorities | There are many changes during the lifespan of a project – the concepts, requirements, number of tasks in a sprint and priorities all can change. Sometimes, a client may change their mind midway through the completion of a given task, which drives up the cost as well. | VH | M | Red | Negative | Consistent and constant communication between team leaders and team members, as well as between team leaders and project clients/stakeholders. Through constant communication, updates can be effectively and efficiently communicated for all project members | Project clients/stakeholders changing project requirements and priorities. | Project change analysis. When changes are made to the project, it’s vital to analyze what impact it has on the current state of the project, how much effort it will take, or if there is risk of delays. The analysis will allow for an efficient division of tasks, updating priorities, and providing the client with accurate information on what can (and cannot) actually be delivered.
3 | Integration of technologies - neg | Many risks are associated with integrations with 3rd party systems, plugins or content management systems. If these technologies and tools are popular and well-known to the team, the risk can be low. If the technology is newer, the risk may increase manyfold. | H | M | Yellow | Negative | Making sure all the tools have proper and updated specifications. Including a decent buffer to the estimate in case there are updates developers haven’t worked with yet. | Adding in new technologies for project functionality | Check if any payment for support is required and include the price in an estimate. Double the time on project learning and document all the issues that surface.
4 | Integration of technologies - pos | Integrating different technologies may bring some risk for onboarding it onto the project, however there are 2 sides to the coin. The investmenet in time and resources for onboarding a new or third-party technology may be worth the investment as it could serve to speed up and optimize parts of the project. | H | H | Red | Positive | Making sure all the tools have proper and updated specifications. Including a decent buffer to the estimate in case there are updates developers haven’t worked with yet. | Adding in new technologies for project functionality | Have support available for any issues and update project timeline as |  | Very high
5 | Design Delay | Design approvals delayed or not submitted on time | L | L | Green | Negative | Making sure prompt follow-up is completed to keep design approvals on schedule. | Design approval not being ready by initial deadline. | Schedule review meetings to quickly get approval and get project back on track. |  | High
6 | Poor Documentation | Not documenting code or other project steps correctly can cause a chaotic environment and waste of time as members familiarize themselves with different parts of the project. | VH | M | Red | Negative | Making sure to allot some time for writing documentation right from the start. Consistently using a specific convention for naming and describing tasks. Must determine what information should always be available. Tools for consideration for documentation include JIRA, Confluence or QA Touch. | Project Team Members showing signs of confusion or getting lost while navigating through parts of the project and/or code. | Many specialized tools are available to help write documentation for APIs and other project deliverables. Good place to start could be Confluence as it is the place where one should be able to find all of the basic project information, team members and their roles, passwords and other access information for important project properties and environment, user descriptions, or list of features. |  | Medium
7 | Launch Day Customer Strain | With a new webiste and potential marketing from the client to customers, there could be an increased strain on servers on the app and wesbite with numbers higher than expected. This is positive because it means there is a good response, just requires proper management. | VH | M | Red | Positive | Always accounting for a buffer above the estimated response for the various software being designed. | Software monitoring inidcates a spike in response when active. | Having a team in place ready to address this specific issue should it arise in order to make sure this risk stays positive. | Impact | Low
8 | Warehouse Overflow | From a high volume of customers, there may be high inventory in response to high demand. The warehouse may begin to fill up in such a case. This is positive because it means there is a good response, just requires proper management. | H | M | Yellow | Positive | Making sure orders are going out as quickly as they are coming in and keeping organized throughout the inventory process. This also requires databases to be operating efficiently so numbers are always up to date. | High volume or traffic through software monitoring. | Having designated space in the warehouse to preapre just in case so that in such a scenario, inventory can still be managed accordingly. |  | Very low
9 | Additional Funding/Grants | It may be beneficial to apply for additional avenues of funding or revenue to help boost the project altogether. However, the risk associated with this action would be the time and resources it may take to locate and follow through with such avenues, and therefore must be accounted for accordingly. | H | M | Yellow | Positive | Making sure the project is staying within the budget consistently so there is no need for additional funding to the project. | Project budget is being questioned or reviewed. | In the case there is additonal funding needed, a plan should be in place to address how to allocate resources to pursue additional funding while not taking a major toll on the project altogether. |  |  | Very low | Low | Medium | High | Very high
10 | Integrating Wireless Functionality throughout the project | The goal of the project is to become mobile and portable. Therefore, high levels of wireless integration are required. The risk associated with this is being vulnerable in a wireless system from events such as a hack on a cloud server or local server, or any other wireless security events. This risk is positive as wireless functionality is a must-have and having it outweighs the associated risk. | VH | H | Red | Positive | Having cyber-security team members and associated cyber-security software to perform constant monitoring for any sign of security events. | Signs of security breaches are present or flagged. | If an event occurs, a cyber-security team must be in place and ready to act quickly to purge all breaches and quickly address any gaps in software in collaboration with other team members. If an event occurs, addressing the event must become a top priority.
11 | Poor Communication | Insufficient time for managers and stakeholders to submit feedback during management review time frames on design requirements, layout, composition of reports and interim reviews | VH | L | Yellow | Negative | Create a interim task, where late feedback reports are gathered and implemented into the workflow | Multiple tasks overlapping, causing decisions of deciding whats of higher concern | If the event occurs, project management must distribute the feedback throughout staggered implementation phases as needed |  |  | Probability
12 | Resource Gathering | Acquiring items critical to project success (e.g., hardware and/or software resources) could be delayed in the procurement process | VH | L | Yellow | Negative | Create a interim task, where a funding request and confirmation transmission is successfully executed | Approval of project requirements not met | If event occurs, any next steps will need to be started, if possible, until the remaining hardware and software resources are gathered
13 | Design Delay | Validating the database design will take longer than anticipated | VH | H | Red | Negative | Put proper steps into place where first time execution of code runs as expected, with no major technical issues | Unforseen design, or lack defined software requirements | Project extenion request will need to submitted for approval
14 | Information Technology | The hardware and software (the development platform) chosen to perform project development, can't handle the workload required to complete the project | M | VL | Green | Negative | Create system tasks that will auto update the system on nightly intervals with critical updates | System upgrades were made during the life cycle of the project, which has caused processing issues | Immediately upgrade the systems as needed, push through all approval requirements
15 | Resources | Risk to cost and schedule involved with the use of subcontractors as a part of the development effort | M | VH | Red | Negative | Express importance of schedule with subcontracting parties, dates cannot be moved | Personal, or unforseen Natural events | Project extenion request will need to submitted for approval, any next steps will need to be started, if possible, until contractor consulting is completed |  |  |  | Risk Matrix
16 | Resource Management | Project management team controls the risk that a project will go over budget, ensuring that the project will be under budget | M | VL | Green | Positive | All deadlines are kept, or completed before the deadline date, well in advance to ensure early project completion | Design, coding and testing are completed sooner that anticipated | If project ends earlier, funds will be reallocated to the next project phase
17 | Marketing | Selling more copies of the widget than anticipated, so the warehouse is swamped with orders | L | L | Green | Positive | Promote the rollout through various traders influenced by the client | Connecting with viable sources | Ensure that we have a high quality product that vendors will want to use and deem essential for business processes
18 | Marketing | Receiving so many signups for our new product that it crashes our website | L | L | Green | Positive | Promote the rollout through various traders influenced by the client | Connecting with viable sources | Prepare for increasing bandwidth, so that the initial rush of bombardment can be obsorbed
19 | Marketing | Getting swamped by press requests because our project is so popular | L | L | Green | Positive | Promote the rollout through various traders influenced by the client | Connecting with viable sources | Prepare press statements of the newly growing business, providing mission and purpose throughout the communities
20 | Client Relations | Change in business strategy by the client could mean additional funding in technology, with a successful rollout | VH | H | Red | Positive | All deadlines are kept, or completed before the deadline date, well in advance to ensure early project completion | Design, coding and testing, and documentation are completed sooner that anticipated | If project ends earlier, funds will be reallocated to the next project phase
21 | Vulnerabilty Design Risk | If design is poorly done then vulnerabilities will be found by bad actors | VH | H | Red | Negative | Hire ethical hackers to do vulnerability testing | Poor network security | Have security team fix the flaw
22 | Vulnerabilty Design Risk | If design is poorly done others may be discovered during a security audit by our ethical hacking team we employ | VH | H | Red | Positive | Ethical hacking team/our cyber sec team will be able to identify addition vulnerabiliteis ahead of time | Poor network security | Have security team fix the flaw
23 | Order Tracking Design Risk | If the design is poorly done then orders could become mixed up | H | M | Yellow | Negative | Have a double checking system to make sure orders are correct | Poor design | Cancel orders and fix flaw in design
24 | Pilot Phase Risk | Trouble finding testers | H | VL | Yellow | Negative | Have people ahead of time willing to test - friends and family could be if theyre objective / could offer incentives for testers | No - shows / low population area / low interest area | Have friends/family test, offer monetary incentive for testers
25 | Training Risk | If trainers are not well versed then the testers may struggle | L | L | Green | Negative | make sure trainers know exactly what they need to show testers | Poor training for trainers | find more qualified trainer, give failed trainer more training
26 | Feedback on bugs | If testing finds bugs then we can fix them before deployment | H | H | Red | Positive | Ask for testers to keep an eye out for bugs | Finding bugs | Fix bugs
27 | Feedback on design | If clients test design then we will receive feedback on it | M | H | Yellow | Positive | Ask testers to note what they do/don’t like about the design | Testing | Consider changing design based on feedback
28 | Word of mouth | If product performs well worth of mouth can help startup | VH | M | Red | Positive | Testers sign NDA | Testing | If feedback is positive ask testers to tell their friends
29 | Training feedback | If trainers do well the product testing will excel | M | M | Yellow | Positive | Make sure trainers have been properly trained | Training | N/A
30 | Word of mouth | If product performs poorly word of mouth could hurt the company | VH | H | Red | Negative | Testers sign NDA | Testing | If feedback is negative NDA will protect company while we fix
Note on C2: If the risk occurs, what will happen to the project?
Note on F2: What is the risk's color code from the risk matrix on the right?
Note on G2: Is this positive risk or a negative risk?
Note on H2: What will you do proactively to address the risk?
Note on I2: How do we know when the risk event has happened? What indications can we look for?
Note on J2: If the event occurs, what can we do to address the effects of the risk?